## Project Budget
Eco-Friendly Water Bottle Project Budget
Category | Role/Item | Details | Calculation | Subtotal
LABOR |  | (All roles: 20 hrs/week * 32 weeks * Rate)
| Project Manager | Rate: $90/hr | 640hrs * $90 | 57600
| Senior Developer | Rate: $95/hr | 640hrs * 95 | 60800
| Back-end Developer | Rate: $75/hr | 640hrs * $75 | 48000
| Front-end Developer | Rate: $70/hr | 640hrs * $70 | 44800
| R&D Lead | Rate: $85/hr | 640hrs * $85 | 54400
| Head of Mfg & Logistics | Rate: $80/hr | 640hrs * $80 | 51200
| Head of Marketing | Rate: $75/hr | 640hrs * $75 | 48000
| Head of Sales | Rate: $70/hr | 640hrs * $70 | 44800
| Design Lead | Rate: $65/hr | 640hrs * $65 | 41600
| Business Analyst | Rate: $60/hr | 640hrs * $60 | 38400
| Tester | Rate: $55/hr | 640hrs * $55 | 35200
| Labor Subtotal |  |  | 524800
SOFTWARE
| Microsoft 365 | 10 users * $12.50/month | Needed from Day 1 (covers full project) | 1000
| ClickUp | 10 users * $12/month | Needed from Day 1 (8 months) | 960
| Adobe CC | $55/month | Needed in Month 2 for 5 months (Design & UI Phase) | 275
| CAD Software | $85 per month | Needed in Month 4 for 3 months (Prototyping Phase) | 255
| Hosting & Domain | $85/month | Needed in Month 6 for 3 months (Testing & Launch) | 255
| Slack/Zoom | 10 users * $8.75/month | Needed from Day 1 (8 months) | 700
| Software Subtotal |  |  | 3445
MATERIALS
| Biodegradable Polymer Pellets | $25/kg | Ordered in Month 5 | For 400kg $10,000
| Silicone for Seals & Lid | $40/kg | Ordered in Month 6 | For 50kg $2,000
| Stainless Steel Cap | $1.50 each | Ordered in Month 7 | For 2,000 units $3,000
| Material Subtotal |  |  | 15000
BUDGET SUMMARY
| Cost Baseline | $524800 + $3,445 + $15000 |  | 543245
| Contingency Reserve | 10% of Cost Baseline ($543,245) |  | 54337
| Budget at Completion (BAC) | Cost Baseline + Contingency |  | 597582
| Management Reserve | 7% of BAC ($597,582) |  | 41830.74
| Total Funding Required | BAC + Management Reserve |  | 639413

## Charts & Visuals
Charts & Visuals
Cost Breakdown
Category | Amount
Labor | 565200
Software | 3445
Materials | 15000
Labor Cost Breakdown
Role | Total Cost
Project Manager | 57600
Senior Developer | 60800
Back-end Developer | 48000
Front-end Developer | 44800
R&D Lead | 54400
Head of Mfg & Logistics | 51200
Head of Marketing | 48000
Head of Sales | 44800
Design Lead | 41600
Business Analyst | 38400
Tester | 35200
Budget Build-Up
Category | Amount
Cost Baseline | 543245
Contingency Reserve | 54337
Management Reserve | 41830.74
Total Funding Required | 639413
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Budget vs Actual
Budget vs Actual
Category | Description | Budget | Actual | Variance
Labor | Project Manager | 57600 | 57600 | 0
Labor | Senior Developer | 60800 | 60800 | 0
Labor | Back-end Developer | 48000 | 48000 | 0
Labor | Front-end Developer | 44800 | 44800 | 0
Labor | R&D Lead | 54400 | 54400 | 0
Labor | Head of Mfg & Logistics | 51200 | 51200 | 0
Labor | Head of Marketing | 48000 | 49200 | -1200
Labor | Head of Sales | 44800 | 45500 | -700
Labor | Design Lead | 41600 | 41600 | 0
Labor | Business Analyst | 38400 | 38400 | 0
Labor | Tester | 35200 | 35200 | 0
Sofware | Microsoft 365 | 1000 | 1000 | 0
Sofware | ClickUp | 960 | 960 | 0
Sofware | Adobe CC | 275 | 275 | 0
Sofware | CAD Software | 255 | 255 | 0
Sofware | Hosting & Domain | 255 | 255 | 0
Sofware | Slack/Zoom | 700 | 700 | 0
Materials | Biodegradable Polymer Pellets | 10000 | 12200 | -2200
Materials | Silicone for Seals & Lid | 2000 | 2000 | 0
Materials | Stainless Steel Cap | 3000 | 3800 | -800
Contingency | Risk/Unexpected Costs | 54374 | 4900 | 49474

## Financial Tracker
Monthly Project Financial Tracker
Category | Description | Budget | Apr Actual | May Actual | Jun Actual | Jul Actual | Aug Actual | Sep Actual | Oct Actual | Nov Actual | YTD Actual | Variance
Labor | Project Manager | 57600 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 57600 | 0
Labor | Senior Developer | 60800 | 7600 | 7600 | 7600 | 7600 | 7600 | 7600 | 7600 | 7600 | 60800 | 0
Labor | Back-end Developer | 48000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 48000 | 0
Labor | Front-end Developer | 44800 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 44800 | 0
Labor | R&D Lead | 54400 | 6800 | 6800 | 6800 | 6800 | 6800 | 6800 | 6800 | 6800 | 54400 | 0
Labor | Head of Mfg & Logistics | 51200 | 6400 | 6400 | 6400 | 6400 | 6400 | 6400 | 6400 | 6400 | 51200 | 0
Labor | Head of Marketing | 48000 | 6000 | 6000 | 6000 | 6240 | 6240 | 6240 | 6240 | 6240 | 49440 | -1440
Labor | Head of Sales | 44800 | 5600 | 5600 | 5600 | 5600 | 5600 | 5800 | 5850 | 5850 | 45500 | -700
Labor | Design Lead | 41600 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 41600 | 0
Labor | Business Analyst | 38400 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 38400 | 0
Labor | Tester | 35200 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 4400 | 35200 | 0
Software | Microsoft 365 | 1000 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 1000 | 0
Software | ClickUp | 960 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 960 | 0
Software | Adobe CC | 275 |  | 55 | 55 | 55 | 55 | 55 |  |  | 275 | 0
Software | CAD Software | 255 |  |  |  | 85 | 85 | 85 |  |  | 255 | 0
Software | Hosting & Domain | 255 | [5 empty] | 85 | 85 | 85 | 255 | 0
Software | Slack/Zoom | 700 | 8.75 | 8.75 | 8.75 | 8.75 | 8.75 | 8.75 | 8.75 | 8.75 | 700 | 0
Material | Biodegradable Polymer Pellets | 10000 |  |  |  |  | 12200 |  |  |  | 12200 | -2200
Material | Silicone for Seals & Lid | 2000 | [5 empty] | 2000 |  |  | 2000 | 0
Material | Stainless Steel Cap | 3000 | [6 empty] | 3800 |  | 3800 | -800
Subtotal | Project Budget | 543245 | 65633.25 | 65688.25 | 65688.25 | 66013.25 | 78213.25 | 68298.25 | 70008.25 | 66208.25 | 548385 | -5140
Contingency | Risk Management Reserve | 54337 | 0 | 0 | 0 | 240 | 2440 | 440 | 1200 | 490 | 4810 | 49527
Grand Total | Total Project Budget | 597582 | 65633 | 65688 | 65688 | 66253.25 | 80653.25 | 68738.25 | 71208.25 | 66698.25 | 553195 | 44387

## Dashboard
Project Financial Health Dashboard
Project Financial Performance Summary
| Total Budget | 597582 |  | KPI | Result
| Total Spent (YTD) | 553195 |  | Total Budget | 597582
| Remaining Budget | 44387 |  | Final Actual Cost | 553195
| Contingency Used | 4810 |  | Final Variance | 44387
| Contingency Remaining | 49527 |  | Contingency Budget | 54337
|  |  |  | Contingency Used | 4810
|  |  |  | Contingency Efficiency | 91.15%
|  |  |  | Largest Cost Overrun | Labor
|  |  |  | Budget Forecast Accuracy | 92.57%
Budget vs. Actual Variance Analysis Chart
| Category | Budget | YTD Actual
| Labor | 524800 | 526940
| Software | 3445 | 3445
| Materials | 15000 | 18000
Monthly Burn Rate
| Month | Total Spent
| April | 65633
| May | 65688
| June | 65688
| July | 66253
| August | 80653
| September | 68738
| October | 71208
| November | 66698